## Sheet1
Brand | Task | Remark | Estimation no of Working Days | Start Date | Delivery Date | Reasons for Delay | Assigned to | Priority | Status
Server | Image caching was specific to origin & host, which is removed |  |  | 2025-03-26 | 2025-03-26 |  | Prafull | High | Done
Server | one of the article apptern was missing the cloudfront cache, introduced the new pattern to make it cache |  |  | 2025-04-02 | 2025-04-02 |  | Abhinesh | High | Done
Server | Set the cloud front cache time 1year for the articles which are 30days (for now just mentioned the id of the last mont's article) |  |  | 2025-04-02 | 2025-04-03 |  | Abhinesh | High | Done
Server | Clear the cache on the Section and Sub-Section pages when an article is updated or published |  |  | 2025-04-02 | 2025-04-02 |  | Prafull | High | Done
Server | Blocked all the .php files on WAF except few selected files in the regex pattern |  |  | 2025-04-01 | 2025-04-03 |  | Prafull, Abhinesh | High | Done
Server | Analysing the server log and blocking the unwanted patterns |  |  | 2025-03-31 |  |  | Abhinesh, Prafull | High | On Going
Page Speed | Improve Accesibility & CLS on Desktop and Mobile |  |  | 2025-04-02 | 2025-04-02 |  | Prafull | High | Done
Page Speed | Experiment Ad script to be loaded after the page loaded | [5 empty] | Prafull | High | On Going
Page Speed | Check any selective Article Page Load by disabling taboola and take the page speed analyssis | [5 empty] | Prafull | High | On Going
Page Speed | Check any selective Article Page Load by disabling Adpushups and take the page speed analyssis | [5 empty] | Prafull | High | On Going
Page Speed | Please check the HomepPageTitle is not called across the site, as editor stopped filling that field | [5 empty] | Abhinesh | High | On Going
Page Speed | Center line the OutstreamAd and Adjust the Advertisement Text | [5 empty] | Abhinesh | High | On Going
SEO | Enalbling the Re-publishing fearured | [5 empty] | Prafull | High | Done
Server | Checking why 404 page is missed from cloud front | [5 empty] | Abhinesh | High | On Going
SEO | Old Menu Appears in Google Serach Console | [5 empty] | Prafull | High | On Going