## Tech
Brand | Task | Remark | Estimation no of Working Days | Start Date | Delivery Date | Reasons for Delay | Assigned to | Priority | Status
Social Media
Data Extraction | Twitter - Without subscription not possible to pull the data, i have tried all possible ways. | Due to some limitations, we can't pull the desired data
Data Extraction | Pinterest - Requested for the limit increase access, waiting for the approval | Due to some limitations, we can't pull the desired data
Data Extraction | snapchat - Cracked the API to pull the data, need to write a script to pull the data in batches | Submitted the data to Sanket |  |  | 2025-06-23 |  |  | High | Done
Data Extraction | IG - Tired with this, tried all the possibilities even submitted the demonstration video, got approved and app is also live, still unable to pull the data | Due to some limitations, we can't pull the desired data
SEO
SEO | Add Sports-life Section on Home Page |  |  | 2025-06-20 | 2025-06-20 |  | Prafull | Medium | Done
SEO | Average response time increased again, check is the issue with Ad | Done |  |  |  |  | Abhinesh | Medium | Done
SEO | INP issue: longer than 200ms (mobile) ( double check ) |  |  | 2025-06-20 | 2025-06-20 |  | Abhinesh | Medium | Done
SEO | Check reference path 404, if it can be tracked from the server | [5 empty] | Abhinesh | Medium | On Going
SEO | Crawl report of www and non www version crawl logs |  |  | 2025-06-23 | 2025-06-23 |  | Abhinesh | High | Done
SEO | Need to create Trend section in homepage similar to TOI above bollywood section | [6 empty] | Low
SEO | Http versions are getting crawled, check if we can get source for this |  |  | 2025-06-23 | 2025-06-23 |  | Prafull | High | Done
Pinkvilla | uae site down |  |  | 2025-06-25 | 2025-06-25 |  | Prafull | High | Done
Pinkvilla | Pinkvilla site country level access and block | Development done |  | 2025-06-25 | 2025-06-25 |  | Prafull | High | Done
Pinkvilla | Articles 410 status update for sports, select, trending, horoscope |  |  | 2025-06-26 | 2025-06-27 |  | Prafull | High | Done
Server | Restrict access to the content management system (CMS) panel over the public internet |  |  | 2025-06-27 |  |  | Prafull | High | On Going
CMS | Introduce multi-factor authentication to the CMS panel. | [5 empty] | Prafull | High | Done
Server | Enable encryption of Elastic Block Store (EBS) volumes to ensure that data is encrypted both at-rest and in-transit (between an instance and its attached EBS storage) | [5 empty] | Prafull | High | Done
Server | Restrict access to its Platform in countries sanctioned by the United States of America or subject to any embargo including but not limited to countries of North Korea, Iran, Iraq, Cuba, Syria, LuhanskDonetsk- Crimea regions of Ukraine, Russia and Belarus.
Server | Establish a comprehensive email authentication, i.e., Sender Policy Framework (SPF), DomainKeys Identified Mail (DKIM), and Domain-based Message Authentication, Reporting, and Conformance (DMARC)
Server | Twitter, Pinterest, IG - Documentation why it is not possible